## Sheet1
Action Item List for Novus CPQ Consulting Blog Post Series
© 2017 Novus CPQ Consulting, Inc. I All Rights Reserved
Area | Action Item | Notes | Owner | Due Date | Answer
Fundamental | Determine what CRM System you will use with your CPQ/QTC Solution | See Blog Posts 1,2,4
| Determine what Routes to Market you need to support | See Blog Posts 2,4
| Determine if you require a Contract Lifecycle Management Solution | See Blog Posts 2,3
| Determine in which system you will create orders and why | See Blog Posts 1,2,3
| Determine if you want to leverage existing systems | See Blog Posts 1,2,3
| Determine the system of record for your business data - Look at Master Data, Transactional Data and Business Logic | See Blog Posts 1,2,3
| Determine if a CPQ or a QTC System is required and why | See Blog Posts 1,2,3 This depends on the breadth of your process needs
| Determine if you have any Industry specific needs that would require and Industry specific Solution | See Blog Post 3 Not every need requires an Industry specific solution and not every Industry will have an industry-specific solution
| Determine what customer you are dealing with (Enterprise, SMB) | See Blog Post 4
Determine your available business transformation budget
Business Requirements | Review current (prioritized) Business Requirement List and confirm required information is available OR make a note on who needs to do what by when to have a final Business Requirements List
| Determine required complexity of your CPQ or QTC Solution. This includes Product Configuration, Pricing, Approvals, Quoting and potentially CLM, Billing and Order Orchestration tasks | See Blog Post 3
| Determine required features and capabilities to achieve your business objectives | See Blog Post 4 Examples are visualization, Artificial Intelligence, NLP for Support
Change Management | Assign Change Management Leader | See Change Management Document
Setup Change Management Plan
Apoint Team Lead for Sales & Marketing
Apoint Team Lead for Sales Operations
Apoint Team Lead for Product Management + Product Engineering + Product Life Cycle Management
Apoint Team Lead for Finance
Apoint Team Lead for IT
Apoint Team Lead for Legal
Project Management | Assign Project Manager / CSM | Basic Project Management considerations for CPQ and QTC Transformation projects
| Agree on PM Methodology | Waterfall, agile or a hybrid of the two. Book Tip: Mike Cohn, Kenneth S. Rubin
Agree on Update Schedule + Forms
Setup Project Plan
Setup Risk Management Plan
| Determine template for Business Requirement Document | Check also this PMI article
Determine template for Functional Requirement Document
Determine template for Technical Requirement Document
Master Data | Identify Owner of Partner Master Data | See Blog Posts 1,2
Identify Owner of Customer Master Data
Identify Owner of Product Master Data
Idenifify Onwer of Pricing Master Data
Identify Owner of Contract Master Data
Idendify owner of CRM - CPQ Data Integration
Idendify owner of CPQ - ERP Data Integration
Product Configuration | Determine who owns which Product / Product Model
Determine who will setup and maintain the Product Model?
Do you need to document the Product Model outside the CPQ tool?
Determine owner for NPI (New Product Introduction) Process and existing product changes
Determine Support owner per Product / Product Model
| Determine owners for Cross Sell and Up Sell (if any) | This may also be done via AI/ML
Determine what information you expect to display in the Configurator UI
Determine Emergency Contact for Product Configuration changes
Pricing | Determine Source of current Pricing Data + Pricing Logic | See Blog Post 1,2,3,4
Determine Price owners per Product / Product Model
| Determine need for VSOE and Finance contact for VSOE | Consider new Revenue Recognition Rules (ASC 606) which will become valid in January 2018 for most public companies
Determine Emergency Contact for Price Changes
Quote | Assign Business owner for Quote Requirements
Determine if and what quote approvals are needed
Check with legal team which Terms & Conditions (T&C) get assigned to what quotes
Determine if legal and budgetary quotes are used
Determine how quote & proposals are planned to work together
Convert Quote-to-Order | Assign Business owner for Convert Quote-to-Order Requirements
Document Order Acceptance Criteria for Products & Services
Reporting & Analytics | Assign Business owner for Reporting & Analytics Requirements
Document current and future KPI’s expected by Sales, Sales Operations, Product Management, Product Engineering, Marketing, Finance and IT
After contract was setup | Determine if you need to use Renewals and if you do changes to a contract after it was signed (e.g. Amending with additional Products, Upgrading to another Product etc.)
Approval Process | Determine required Quote Discount Approvals
Determine how you plan to approve Quotes
Determine if you want to prevent Sales Reps from generating Quote Documents before they have all required approvals